## Slide 1: Meeting 03/13/2020
Naudé Conradie
19673418

## Slide 2: Theoretical Work
Code
  Changes to pipeline
    Removed NX
    Create geometry in Marc
  Results
    Displacement
    Strain
    Stress
    Maximum values & top right corner

## Slide 3: Quarterly Report
Feedback
  2. Literature review
    Add images for clarification
    Examples of L-systems and CPPNs
  3. Material Testing
    Cover methods and materials
    Include simulation processes
    Code
  4. Software
    Elaborate on 4.1 and 4.2
    Reduce tables
    Work breakdown structure

## Slide 4: Work Breakdown Structure
March
  Complete literature review
  Complete material testing on Mold Star 15
  Complete material testing chapter
  Complete and refine code for current model
  Start implementing L-systems to obtain unique sub-units
April
  Implement material model from material testing
  Complete software chapter according to progress
  Complete implementation of L-systems
  Complete testing other materials

## Slide 5: Work Breakdown Structure
May
  Start implementing CPPNs for obtaining larger units
  Implement other material models
  Complete software chapter according to progress
June
  Complete main code structure
  Construct test units
  Start with chapter discussing results

## Slide 6: Practical Work
Compression grip designs
  Drawing standards
Aluminium angles
  Sample flattening

## Slide 7: General Admin
Literature search SUNLearn course
Work from home setup